## Pipeline & Status Per Region
Pipeline Report
Job # | Project Name | City | State | Zip | # Units | Anticipated Start Date | Months Duration | Bid Status | Drawing Status | Building Type | PCM | SPM | Area | Subs | Contact Info | Manf. Bid | Awarded
Pipeline Update: 04/24/23
Multifamily Bidding Project Status
Midwest Region
P23-277 | IN, Fishers, USA Parkway, 3 | Fishers | IN | 46038 | 261 | 2024-04-09 | 25 | Upcoming Project | Site Plan | Metro 4 Story | Aaron | Mike | Indy
P23-277 | IN, Fishers, USA Parkway, 3 (Retail) | Fishers | IN | 46038 |  | 2024-10-02 | 5 | Upcoming Project | Dark Shell | Single Story | Aaron | Mike | Indy
Southeast Region
P23-271 | FL, Sarasota, Fruitville Rd. | Sarasota | FL | 32240 | 257 | 2023-05-29 | 21 | Post Bid | Addendum D | Metro 4 Story | Josh | Darren | SW Florida | Babes Plumbing G&M GWB, Inc. MPA Plumbing Southwest Plumbing Services Horizon Next Gen Plumbing Wright Bros. Miller Mech. | 941-488-2402 912-444-0934 dawn@gwb-inc.com 813-513-0030 305-232-6203 843-982-0413 843-816-9200 vsingh@wrightbrotherscs.com 770-952-3864 | ? Delta ? ? ? Delta/Kohler ? ? Delta | G&M
P23-284 | FL, North Port, Sumter Blvd. | North Port | FL | 34286 | 268 | 2023-08-28 | 30 | Upcoming Project | 80% Set | Villas | Josh | Darren | SW Florida
P23-281 | FL, Pensacola, Nine Mile Rd. | Pensacola | FL | 32513 | 324 | 2023-05-30 | 23.5 | Bidding | Addendum C | Classic 3 Story | Aaron | Darren | Panhandle | G&M GWB Horizon Solomon | 912-444-0934 dawn@gwb-inc.com 843-982-0413 248-486-1600 | Delta ? Delta ? | Solomon
P23-291 | FL, Rockledge, Fiske Blvd. | Rockledge | FL | 32955 | 380 | 2023-06-19 | 30 | Bidding | Addendum C | Select | Charles | Darren | Central FL | Classic Works Services G&M Kimble Solomon Plumbing Sunshine State Plumbing Horizon NexGen | 352-233-1153 912-444-0934 479-756-1099 248-486-1600 904-262-1066 843-982-0413 843-816-9200 | ? Delta ? ? Proflo Delta ?
P23-299 | SC, Myrtle Beach, Legends Rd. | Myrtle Beach | SC | 29579 | 300 | 2024-02-21 | 23.8 | Upcoming Project | SD Set | Select/Premium | Charles | Darren | Myrtle Beach
P23-304 | GA, Union City, Derrick Rd | Union City | GA | 30291 | 276 | 2023-12-18 | 23 | Upcoming Project | SD Set | Premium | Charles | Darren | SW Atlanta
P23-280 | FL, Lady Lake, 135 Crossing | Lady Lake | FL | 32158 | 300 | 2023-06-19 | 21 | Bidding | Addendum C | Classic | Nate | Darren | Central FL | ARR Plumbing G&M Horizon JA Croson MPA Plumbing Ross Solomon Plumbing SR Plumbing Sunshine State Wright Bros. | 407-350-5017 912-444-0934 843-982-0413 813-513-0030 352-728-6053 248-486-1600 407-275-9614 904-262-1066 vsingh@wrightbrothersscs.com | ? Delta Delta Moen/Delta ? ? ? VE? ? Per Plans
P23-307 | FL, Bradenton, El Conquistador Pkwy | Bradenton | FL | 34210 | 279 | 2024-01-30 | 20 | Upcoming Project | SD Set | Metro | Charles | Darren | SW Florida
P23-309 | FL, Vero Beach, 11th Dr. | Vero Beach | FL |  | 276 | 2024-02-01 | TBD | Upcoming Project |  | Premium | Josh | Darren | SE Florida
P23-308 | GA, Pooler, Pooler Pkwy | Pooler | GA | 31322 | 344 | 2024-01-03 | 26.3 | Upcoming Project | Site Plan | Select/Premium | Josh | Darren | Savannah, GA
West Region
P21-233 | CO, Fountain, Metropolitan Rd. | Fountain | CO | 80817 | 336 | 2023-03-22 | 24.5 | Post Bid | Addendum C | Classic 3 Story | Jared | John | South Denver | G&M Kimble Horizon SSLLC UMC Inc. NIKSIC | 912-444-0934 479-756-1099 843-982-0413 scott@ssllc.pro joe.whitford@umc.us niksicpluestimator@gmail.com | Delta Delta ? ? Per Plans ? | Kimbel
P23-247 | CO, Greeley, Centerplace Drive | Greeley | CO | 80550 | 336 | 2023-01-16 | 24 | Post Bid | Addendum C | Classic 3 Story | Nate | Mike | North Denver | G&M Kimble Horizon SSLLC JT Plumbing Villa Plumbing NIKSIc Rocky Mountain Plumbing | 912-444-0934 479-756-1099 843-982-0413 scott@ssllc.pro 970-818-1613 ? niksicpluestimator@gmail.com 970-532-2020 | Delta Delta ? ? ? ? ? Delta | Horizon
P22-244 | CO, Broomfield, 120th Ave. | Broomfield | CO | 80020 | 360 | 2024-01-12 | 30.8 | Upcoming Project | SD Set | Classic 3 Story | Nate | Mike | Denver
P23-279 | CO, Fort Collins, Spaulding Rd. | Fort Collins | CO | 80524 | 360 | 2024-04-19 | 26.5 | Upcoming Project | SD Set | Select/Villas | Aaron | Mike | North Denver
P23-276 | CO, Wheat Ridge, Kipling St. | Wheat Ridge | CO | 80033 | 254 | 2023-12-04 | 20 | Upcoming Project | 95% Set | Metro 4 Story | Nate | Mike | Denver
P23-254 | CO, Longmont, Hover St. | Longmont | CO | 80501 | 276 | 2024-08-28 | 23 | Upcoming Project | Conceptual Plan | Classic | Aaron | Mike | North Denver
P23-253 | CO, Fort Collins, Vine Rd. | Fort Collins | CO | 80521 | 336 | 2024-02-09 | 30 | Upcoming Project | SD Set | Classic 3 Story | Nate | Mike | North Denver
P23-261 | AZ, Buckeye, Yuma Rd. | Buckeye | AZ | 85326 | 252 | 2023-01-16 | 23 | Post Bid | Addendum C | Classic 3 Story | Josh | John | Phoenix | Arizona Plumbing Specialists Horizon Iron Horse Jet Industries JFN Mechanical | hunterudall.aps@gmail.com 843-982-0413 480-830-2865 503-932-7572 ? | ? ? Pfister ? ? | JFN Mechnical
P22-250 | AZ, Phoenix, Dove Valley Rd. | Phoenix | AZ | 85002 | 224 | 2023-09-20 | 23.8 | Upcoming Project | Addendum B | Metro 4 Story | Jared | John | Phoenix | Arizona Plumbing Specialists Horizon Hyman Iron Horse JBS Jet Industries JFN Mechanical Red Oak | hunterudall.aps@gmail.com 843-982-0413 979-836-1764 480-830-2865 623-587-4828 503-932-7572 ? 480-494-5747 | ? ? Mix Pfister Pfister ? ? ?
23-266 | AZ, Gilbert, Germann Rd. (Retail) | Gilbert | AZ | 85297 |  | TBD | 13 | Upcoming Project |  | Metro/Mixed Use | Nate | John | Phoenix
P23-266 | AZ, Gilbert, Germann Rd. | Gilbert | AZ | 85297 | 300 | 2024-04-01 | 26 | Upcoming Project | Addendum B | Metro/Mixed Use | Nate | John | Phoenix
P23-257 | AZ, San Tan Valley, Gary Rd. | San Tan Valley | AZ | 85140 | 308 | 2023-06-19 | 24 | Bidding | Addendum B | Classic | Jared | John | Phoenix | CHS Jet Industries Red Oak | 480-615-6018 503-932-7572 480-494-5747 | ? Per P Sheets Per P Sheets
P23-252 | UT, Salt Lake City, Saratoga Springs | Salt Lake City | UT | 84045 | 300 | TBD | 25.5 | Upcoming Project | Gut Check | Select | Nate | John | Saratoga Springs
P23-296 | CO, Monument, Higby Rd. | Monument | CO | 80132 | 276 | 2023-11-28 | 21 | Upcoming Project | Site Pan | Classic | Jared | John | South Denver
| Multifamily Pipeline Totals |  |  |  | 7183 | Units
(PCM) Preconstruction Managers | [5 empty] | (SPM) Sub Procurement Manager
Aaron Richmond ¦ (812) 242-1154 ¦ arichmond@thompsonthrift.com | [5 empty] | Darren Lambert ¦ (463) 237-3273 ¦ dlambert@thompsonthrift.com
Joshua Revesz ¦ (812) 514-8510 ¦ jrevesz@thompsonthrift.com | [5 empty] | John Williams ¦ (463) 237-3282 ¦ jwilliams@thompsonthrift.com
Nate Williams ¦ (812) 514-8639 ¦ nwilliams@thompsonthrift.com | [5 empty] | Mike Biggerstaff ¦ (812) 242-1145 ¦ mbiggerstaff@thompsonthrift.com
Jared Ruehrschneck ¦ (812) 242-1181 ¦ jruehrschneck@thompsonthrift.com
Charles Creisher ¦ (317) 853-5471 ¦ ccreisher@thompsonthrift.com
Classic = 3story garden
Metro = 4 story double loaded Garden
Villa = Single family for Rent Duplex
Select = 2 story direct access