## ConstructionRpt
Construction Project Schedule
12/1/2022 9:41:20 AM
| Prop ID | Property | Address | City | State | Zip | Units | Const PM | Property Type | Construction Contractor | Architect | Architect Contact | Bid Due Date | Start Date | Est Finish Date
New Construction
Active
| 800 | Upper Post Flats (Fort Snelling) | 6365 Sibley Ave | Fort Snelling | MN | 55111 | 191 | Keith Richters | Family, S42, Townhome | Weis Builders | BKV | Mike Krych | 2019-09-01 | 2021-06-25 | 2023-10-02
| 690 | South Range Crossings (fka Stroh Ranch) | 19130 J Morgan Blvd | Parker | CO | 80134 | 204 | Marty Tuttle | Family, S42 | Bryan Construction | PWN | Jason Weber | 2020-02-15 | 2020-08-06 | 2023-01-20
| 991 | Orville Commons (fka Woodbury Family - Radio Drive) | 4290 Radio Drive | Woodbury | MN | 55129 | 235 | Marty Tuttle | Family, S42 | Eagle Builders | BKV | Chris Palkowitsch | 2021-11-11 | 2022-01-14 | 2023-07-06
| 692 | Willow Place (fka McDonough Senior) | 150 Cola Welch Parkway | McDonough | GA | 30253 | 182 | Ashley Sweat | S42, Senior | WD Construction | Martin Riley Associates | Michael Lee |  | 2021-10-22 | 2023-06-01
|  | Homeward Pikes Peak - Phase I - Pro Bono | Colorado | Colorado Springs | CO | 80909 | 0 | Marty Tuttle | Family | Bryan Construction | E+A | Paul Hohmann | 2021-01-29 | 2021-09-13 | 2023-10-19
| 809 | Vista Ridge (fka NWC of 19th & Southern Ave Land Site) | 2050 West Southern Avenue | Phoenix | AZ | 85041 | 308 | Sean Imani | Family, Garden, Max Rent, S42 | WD Construction | Todd & Associates | Gary Todd | 2019-10-01 | 2021-06-09 | 2023-06-29
| 811 | Sandpiper Glen (fka Orlando Senior) | 8780 Donnybrook Drive | Orlando | FL | 32825 | 288 | Bob Jensen | S42, Senior | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2022-05-18 | 2024-05-02
| 698 | Harbor at Twin Lakes (fka Roseville Senior) | 2730 Herschel Street North | Roseville | MN | 55113 | 277 | Marty Tuttle | S42, Senior | Eagle Builders | BKV | Mike Krych |  | 2021-07-15 | 2022-12-30
| 804 | Osprey Park (fka Osprey Village) | 151 N. Osprey Park Road | Kissimmee | FL | 34758 | 383 | Bob Jensen | S42, Senior | WD Construction | Bessolo Design Group | Kevin Bessolo | 2020-11-30 | 2021-07-29 | 2023-08-17
| 814 | Heron Ridge (fka Kissimmee Senior) | 4351 Little Egret Road | Kissimmee | FL | 34746 | 331 | Bob Jensen | S42, Senior | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2022-01-25 | 2023-12-18
| 810 | Ashlynn Ridge (fka Newnan GA Senior) | 2001 Newnan Crossing Bypass | Newnan | GA | 30263 | 202 | Tamra Peters | S42, Senior | WD Construction | Martin Riley Associates | Michael R. Lee | 2020-09-04 | 2021-04-06 | 2022-11-25
| 693 | Promenade (fka McDonough Family) | 155 Cola Welch Parkway | McDonough | GA | 30253 | 288 | Ashley Sweat | Family, S42 | WD Construction | Martin Riley Associates | Jackie Martin |  | 2021-10-22 | 2023-09-18
| 822 | Casa Azure (fka Desert Sky Mall Senior) | 7750 W. Encanto Blvd | Phoenix | AZ | 85035 | 196 | Sean Imani | S42 | WD Construction | Todd & Associates | Doug Sexton |  | 2022-04-12 | 2023-12-11
| 813 | Paramount (fka Greenbriar Family) | 3223 Greenbriar Parkway SW | Atlanta | GA | 30331 | 240 | Tamra Peters | Family, S42 | HJ Russell & Company | Bessolo Design Group | Kevin Bessolo |  | 2022-04-06 | 2023-12-06
| 430 | The Meridian (fka Dekalb Workforce) | 2170 Cook Road | Decatur | GA | 30032 | 217 | Ashley Sweat | S42 | WD Construction | Martin Riley Associates | Diane Giordano |  | 2022-05-18 | 2023-11-01
| 815 | 900 at Cleveland Park (fka 900 Dickerson Pike) | 900 Dickerson Pike | Nashville | TN | 37207 | 256 | Keith Richters | Family, S42 | WD Construction | Smith Gee Architects | Scott Morton |  | 2021-12-23 | 2024-06-08
| 812 | Briar Park (fka Greenbriar Senior) | 3263 Greenbriar Parkway SW | Atlanta | GA | 30331 | 244 | Tamra Peters | S42, Senior | HJ Russell & Company | Bessolo Design Group | Kevin Bessolo |  | 2022-04-06 | 2023-12-06
|  | JCMH - Pro Bono | Jefferson County | Jefferson County | CO | 80001 | 0 | Marty Tuttle | S8 | Bryan Construction | E+A | Paul Hohmann |  | 2022-11-03 | 2023-10-30
| 821 | Aviara Flats (fka Desert Sky Mall Family) | 7800 W. Encanto Blvd | Phoenix | AZ | 85035 | 372 | Sean Imani | S42 | WD Construction | Todd & Associates | Doug Sexton |  | 2022-04-12 | 2024-08-01
| 838 | Haven at Congaree Pointe (fka Columbia Senior) | 2401 Atlas Road | Columbia | SC | 29209 | 198 | Steven Trainer | Senior | WD Construction | Martin Riley Associates | Diane Giordano |  | 2022-04-06 | 2023-12-07
4612
Completed - Retention
| 686 | Heritage at Church Ranch (fka Legends of Church Ranch) | 10050 Wadsworth Blvd | Westminster | CO | 80021 | 205 | Marty Tuttle | S42, Senior | Bryan Construction | PWN | Pat Nook | 2020-02-15 | 2020-04-29 | 2022-06-08
| 691 | Centennial Crossings (fka Legends of Centennial) | 15475 East Fair Place | Centennial | CO | 80016 | 209 | Marty Tuttle | S42, Senior | W.E. O'Neil | PWN | Jason Weber | 2020-03-27 | 2020-09-09 | 2022-06-08
| 963 | Scharbauer Flats (fka Ventura at Fairgrounds) | 1915 E Scharbauer Dr. | Midland | TX | 79705 | 300 | Steven Trainer | Family, Garden, S42 | MW Builders | BKV | Keith Traywick | 2019-06-14 | 2020-07-07 | 2022-06-08
| 801 | Oaks Landing | 700 7th St NW | New Brighton | MN | 55112 | 204 | Marty Tuttle | S42, Senior | Eagle Builders | BKV | Mike Krych | 2019-08-27 | 2021-01-05 | 2022-07-06
| 445 | Preserve at Peachtree Shoals | 2995 Old Peachtree Road | Dacula | GA | 30019 | 240 | Keith Richters | S42, Senior | Flournoy Construction | Martin Riley Associates | Mike Riley | 2020-05-22 | 2020-07-06 | 2022-11-25
| 446 | Grayson Ridge | 1466 Grayson Highway | Lawrenceville | GA | 30045 | 240 | Keith Richters | S42, Senior | HJ Russell & Company | Martin Riley Associates | Mike Riley | 2020-03-01 | 2020-07-06 | 2022-05-02
| 447 | Reef at Riviera (fka Palmetto Senior) | 751 Haben Boulevard | Palmetto | FL | 34221 | 224 | Bob Jensen | S42, Senior | Current Builders | Bessolo Design Group | Kevin Bessolo | 2019-07-01 | 2020-05-08 | 2022-11-03
| 432 | Legacy Commons at Signal Hills (fka Senior Kmart Site) | 45 Butler Avenue, East | West St. Paul | MN | 55118 | 247 | Marty Tuttle | Family, S42, Senior | Weis Builders | BKV | Mike Krych | 2020-06-12 | 2021-01-27 | 2022-09-02
|  | Gainesville, FL - Pro Bono |  | Gainesville | FL |  | 0 | Bob Jensen | S42, Senior | Verdex | Ted Hoffman Jr. Architect P.A. | Ted Hoffman | 2020-05-15 | 2020-12-26 | 2022-09-14
| 431 | Hilltop at Signal Hills (fka Family Kmart Site) | 15 Butler Avenue East | West St. Paul | MN | 55118 | 146 | Marty Tuttle | Family, Max Rent, S42 | Weis Builders | BKV | Mike Krych | 2020-06-01 | 2021-01-25 | 2022-07-14
2015
Pending
| 628 | Austin, TX - New Construction - Sage at Franklin Park (Woodway Land) | 4600 Nuckols Crossing Road | Austin | TX | 78744 | 0 | TBD - OR | S42, Senior | TBD |  |  |  | 2023-07-10 | 2025-07-01
| 806 | Estrella Springs (fka Goodyear - Family) | SEC Van Buren Street & South Cotton Lane | Goodyear | AZ | 85338 | 396 | Sean Imani | Family, Garden, S42 | WD Construction | Todd & Associates | Brent Fike |  | 2023-02-13 | 2025-06-02
| 807 | Suncrest Vista (fka Goodyear - Senior) | SEC Van Buren Street & South Cotton Lane | Goodyear | AZ | 85338 | 261 | Sean Imani | Garden, S42, Senior | WD Construction | Todd & Associates | Brent Fike |  | 2023-02-13 | 2025-06-02
| 818 | Surprise, AZ - Senior | SWC Cotton Lane & Waddell Road | Phoenix | AZ | 85374 | 216 | Sean Imani | S42 | WD Construction | Todd & Associates | Brent Fike |  | 2023-08-08 | 2024-09-01
| 852 | Aurora Metro Center | 15008 E Metro Center Ave | Aurora | CO | 80012 | 222 | Marty Tuttle | S42, Senior | WD Construction | Todd & Associates | Clames Ternoski |  | 2023-05-05 | 2024-12-05
|  | Golden Gate - Pro Bono | 4100 Golden Gate Pkwy | Naples | FL | 34116 | 0 | TBD - OR | Family, Garden | TBD | TBD | TBD |  | 2022-10-01 | 2025-05-01
| 817 | Surprise, AZ - Family | SWC Cotton Lane & Waddell Road | Phoenix | AZ | 85374 | 392 | Sean Imani | S42 | WD Construction | Todd & Associates | Brent Fike |  | 2023-08-08 | 2025-04-01
| 868 | Arlington, TX - 6900 Matlock | 6900 Matlock Road | Arlington | TX | 76002 | 192 | Steven Trainer | Family, Garden, S42 | WD Construction | BKV | Matt Nugent |  | 2023-02-02 | 2024-07-02
| 833 | Anchors at Gulf Harbors ( fka New Port Richey, FL - Senior) | 5274 Sea Forest Drive | New Port Richey | FL | 34652 | 387 | Bob Jensen | S42, Senior | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2023-08-01 | 2025-08-04
| 853 | Creekridge on the Park (fka Charlotte Family) | 7800 Creekridge Rd | Charlotte | NC | 28212 | 150 | TBD - OR | Family, S42 | WD Construction | BKV | Mat Nugent |  | 2023-03-15 | 2023-12-13
| 880 | Chandler, AZ - Family New Construction | E/NEC Arizona Ave & Ocotillo | Chandler | AZ | 85286 | 182 | TBD - OR | Family, S42 | TBD | Todd & Associates | Gary Todd |  | 2023-08-08 | 2025-06-01
| 879 | Chandler, AZ - Senior New Construction | E/NEC Arizona Ave & Ocotillo | Chandler | AZ | 85286 | 336 | TBD - OR | S42, Senior | TBD | Todd & Associates | Gary Todd |  | 2023-08-08 | 2025-06-01
| 855 | The Mira | 1255 Plymouth Sorrento Rd | Apopka | FL | 32712 | 312 | Keith Richters | Family, S42 | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2023-11-10 | 2025-10-03
| 854 | The Waters | 1277 Plymouth Sorrento Rd | Apopka | FL | 32712 | 180 | Keith Richters | S42, Senior | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2023-11-10 | 2025-10-03
| 856 | Rio Rancho, NM - Family - Camino Encantadas & Oersted | Camino Encantadas & Oersted | Rio Rancho | NM | 87144 | 216 | Marty Tuttle | Family, S42 | WD Construction | Todd & Associates | Doug Sexton |  | 2023-06-01 | 2025-06-02
| 849 | Percival Place (fka Columbia, SC - Family) (2311 Percival Rd) | 2311 Percival Road | Columbia | SC | 29223 | 180 | TBD - OR | Family | WD Construction | BKV | Mike Krych |  | 2023-04-10 | 2023-12-15
| 846 | 67 Flats (fka Glendale - Family) | 6504 North 67TH Ave | Glendale | AZ | 85301 | 360 | Sean Imani | Family, S42 | WD Construction | Todd & Associates | Brent Fike |  | 2023-05-31 | 2025-09-30
| 847 | Marana, AZ - Family - 8695 N Silverbell Road | 8695 N Silverbell Road | Marana | AZ | 85743 | 200 | TBD - OR | Family, S42 | WD Construction | Todd & Associates | Brent Fike |  | 2023-03-31 | 2025-03-31
| 859 | Avery Landing (fka Greenville, SC - 6615 Augusta Rd) | 6615 Augusta Road | Greenville | SC | 29605 | 168 | TBD - OR | S42 | WD Construction | BKV | Mathew Nugent |  | 2023-04-10 | 2025-04-05
| 845 | Juniper Square (fka Glendale - Senior) | 6504 North 67TH Ave | Glendale | AZ | 85301 | 221 | Sean Imani | Family, S42, Senior | WD Construction | Todd & Associates | Brent Fike |  | 2023-05-31 | 2025-05-31
| 871 | Harmony at Congaree Pointe (fka Columbia - Family - Atlas Road) - Phase I | Atlas Road | Columbia | SC | 29209 | 336 | TBD - OR | Family | TBD | TBD | TBD |  | 2024-01-08 | 2025-08-01
| 870 | Jessamine (fka Trenholm Road Senior) | 0 Trenholm Road | Dentsville | SC | 29223 | 240 | TBD - OR | S42 | WD Construction | BKV | Mike Krych |  | 2023-01-12 | 2024-08-05
|  | Santa Fe, NM - New Construction - 1-25 & Cerrillos Road - Family | 1-25 & Cerrillos Road | Santa Fe | NM | 87508 | 312 | TBD - OR | Family, Garden, S42 | TBD | TBD | TBD |  | 2024-01-01 | 2025-04-01
|  | Dentsville, SC - Family - Intersection of Trenholm Rd and O'Neil Court | Intersection of Trenholm Rd and O'Neil Court | Dentsville | SC | 29223 | 192 | TBD - OR | Family, S42 | WD Construction | BKV | Mike Krych |  | 2023-06-30 | 2024-08-05
|  | Hamilton, OH - New Construction - 7551 Gateway Ave - Senior | 7551 Gateway Ave | Hamilton | OH | 45011 | 244 | TBD - OR | S42, Senior | TBD | TBD | TBD |  | 2024-03-01 | 2025-09-01
| 874 | Maison at Solivita Marketplace | 4755 Laurel Avenue | Kissimmee | FL | 34758 | 396 | TBD - OR | Family, S42 | WD Construction | Bessolo Design Group | Kevin Bessolo |  | 2023-07-10 | 2025-03-28
|  | Holiday, FL - New Construction - Anclote High - Family | Anclote High | Holiday | FL | 34691 | 300 | TBD - OR | Family, S42 | TBD | Bessolo Design Group | Kevin Bessolo |  | 2023-09-01 | 2025-09-01
|  | Firestone, CO - New Construction - SE of Colorado Blvd & Firestone Blvd - Family | SE of Colorado Blvd & Firestone Blvd | Firestone | CO | 80504 | 322 | TBD - OR | Family, S42 | TBD | Todd & Associates | Brent Fike |  | 2023-11-01 | 2024-10-17
| 881 | Caldwell, ID - New Construction - 22689 Farmway Rd - Family | 22689 Farmway Road | Caldwell | ID | 83607 | 240 | TBD - OR | N/A | TBD | TBD | TBD |  | 2024-01-01 | 2025-12-01
7153
|  | New Construction Project Subtotal |  |  |  |  | 13780
Rehab
Active
| 827 | Hickory Manor - Resyndication | 1626 Old Hickory Trail | Desoto | TX | 75115 | 190 | Steven Trainer | Max Rent, S42, Senior | DCAS | C&A | Rebekah Gurule | 2022-09-09 | 2022-07-01 | 2023-05-24
| 851 | Park Manor - Resyndication | 1725 S FM Road 1417 | Sherman | TX | 75092 | 196 | Steven Trainer | Max Rent, S42, Senior | DCAS | C&A | Tony Blume | 2022-05-01 | 2022-08-10 | 2023-03-01
| 825 | Lakeside Pointe – Resyndication | 2920 Oak Road | Pearland | TX | 77584 | 274 | Steven Trainer | Market, S42 | Langerman | C&A | Tony Blume | 2022-03-18 | 2022-10-12 | 2023-10-02
| 850 | Lakeside Manor - Resyndication | 902 West Eldorado Parkway | Little Elm | TX | 75068 | 176 | Yao Wang | S42, Senior | DCAS | E+A | Justin Robben |  | 2022-08-10 | 2023-11-11
| 842 | Mission at Baytown | 6033 Garth Road | Baytown | TX | 77521 | 250 | Steven Trainer | Garden, S42 | Langerman | C&A | Tony Blume | 2022-07-13 | 2022-07-20 | 2024-03-01
| 878 | Chapel Ridge of Gallatin Resyndication | 1590 Airport Road | Gallatin | TN | 37066 | 208 | Keith Richters | Family, Garden, S42 | Community Construction Group | E+A | Justin Robben |  | 2022-09-20 | 2023-05-24
1294
Completed - Retention
| 967 | Park Avenue West - Resyndication | 827 Park Avenue West | Denver | CO | 80205 | 122 | Marty Tuttle | Family, S42 | Katerra | C&A | Dan O'Mara | 2019-03-01 | 2019-12-03 | 2022-01-17
| 823 | Riverstation (fka Signature at Trinity River) - Resyndication | 220 Stoneport Drive | Dallas | TX | 75217 | 236 | Adam Brookins | Family, Garden, S42 | DCAS | C&A | Sean Goodemote | 2020-01-01 | 2021-09-01 | 2022-10-20
| 649 | Woodway Village - Resyndication | 4600 Nuckols Crossing Road | Austin | TX | 78744 | 160 | Adam Brookins | Family, Garden, Townhome | Legacy Construction | E+A | Jeremy Floarke | 2020-06-05 | 2020-08-18 | 2022-05-02
| 828 | Knolls at West Oaks - Internal Resyndication (fka City Parc at West Oaks) | 3443 Addicks Clodine Road | Houston | TX | 77082 | 168 | Steven Trainer | Family, S42 | Langerman | C&A | Rebekah Gurule | 2021-07-14 | 2021-09-21 | 2022-11-01
686
Pending
| 843 | Rosemont at Mayfield Villas | 2002 Mayfield Villa Drive | Arlington | TX | 76014 | 280 | Bill Buelow | Family, S42 | DCAS | C&A | Tony Blume | 2022-11-15 | 2022-12-08 | 2023-11-30
| 803 | Woodway Square - Resyndication | 1700 Teri Road | Austin | TX | 78744 | 240 | Steven Trainer | S42 | TBD | E+A | Jeremy Floarke |  | 2023-05-01 | 2024-05-01
| 840 | Garland, TX - The Cesera | 202 North Belt Line Road | Garland | TX | 75040 | 204 | TBD - OR | S42, Senior | TBD | E+A | Justin Robben |  | 2023-02-27 | 2024-06-01
| 841 | Pasadena, TX - The Portofino (fka Primrose of Pasadena) | 2122 East Sam Houston Parkway South | Pasadena | TX | 77503 | 248 | TBD - OR | S42, Senior | TBD | E+A | Justin Robben |  | 2023-04-01 | 2024-04-01
| 864 | Fort Myers, FL - Aria Landings I (FKA The Brittany I) | 4050 Winkler Avenue Extension | Fort Myers | FL | 33916 | 208 | Bob Jensen | S42 | TBD | E+A | Justin Robben |  | 2023-05-22 | 2023-11-23
| 837 | Oaks at Saint John - Resyndication | 210 Nettles Lane | Pointe Verda Beach | FL | 32081 | 160 | Tamra Peters | Family, S42 | Community Construction Group | C&A | Rebekah Gurule | 2022-06-01 | 2023-02-10 | 2023-05-26
| 877 | Oak Meadows - Cocoa, FL | 1605 Flower Mound Lane | Cocoa | FL | 32922 | 120 | TBD - OR | S42 | TBD | TBD | TBD |  | 2023-12-29 | 2025-01-01
| 865 | Fort Myers, FL - Aria Landings II (FKA The Brittany II) | 4050 Winkler Avenue Extension | Fort Myers | FL | 33916 | 112 | Bob Jensen | Family, S42 | TBD | E+A | Justin Robben |  | 2023-03-23 | 2024-01-23
|  | Cape Coral, FL - Crossings at Cape Coral - Resyndication | 1150 Hancock Creek S Blvd | Cape Coral | FL | 33909 | 168 | TBD - OR | Family, S42 | TBD | E+A | Justin Robben | 2022-04-28 | 2023-01-13 | 2024-08-05
1740
|  | Rehab Project Subtotal |  |  |  |  | 3720
Self Performed
Active
| 450 | 808 Berry Place - Refinance - 2021 | 808 Berry Street | St. Paul | MN | 55114 | 267 | Bill Buelow | Family | DCAS | BKV | Liza Kapisak |  | 2021-03-01 | 2023-04-03
| 453 | Landings at Silver Lake Village - Refinance - 2021 | 2551 38th Ave. NE | St. Anthony | MN | 55421 | 263 | Bill Buelow | N/A | DCAS | BKV | Liza Kapisak |  | 2021-03-10 | 2023-06-02
| 834 | Groves of Lawrenceville (fka Greens at Hillcrest) | 850 Hillcrest Green Drive NW | Lawrenceville | GA | 30046 | 176 | Bill Buelow | S42 | DCAS | C&A | Rebekah Gurule |  | 2021-07-29 | 2022-12-01
| 970 | Highland Hills - 2021 Refinance | 3131 Simpson Stuart Road | Dallas | TX | 75241 | 250 | Adam Brookins | S42 | DCAS | N/A | N/A |  | 2022-05-03 | 2023-01-02
| 969 | Five Mile Creek - 2021 Refinance | 5151 Village Fair Drive | Dallas | TX | 75224 | 236 | Adam Brookins | Family, S42 | DCAS | N/A | N/A |  | 2022-05-03 | 2023-01-02
| 829 | Swiss View | 455 Swiss Ave | Nashville | TN | 37211 | 32 | Adam Brookins | Family, Garden, S42 | DCAS | N/A | N/A |  | 2021-06-28 | 2023-01-31
| 836 | Flats on Water’s Edge (fka Lakeside) - Acquisition Rehab | 3940 Bell Road | Hermitage | TN | 37076 | 156 | Adam Brookins | Family, Garden, S42 | DCAS | N/A | N/A |  | 2021-10-04 | 2023-02-28
| 835 | Groves of Lawrenceville II | 850 Hillcrest Green Drive NW | Lawrenceville | GA | 30046 | 146 | Bill Buelow | Family, S42 | DCAS | C&A | Rebekah Grule |  | 2022-07-19 | 2022-12-01
| 844 | Alexander at Stonecrest | 100 Leslie Oaks Drive | Lithonia | GA | 30058 | 262 | Bill Buelow | S42 | DCAS | C&A | Rebekah Gurule |  | 2022-01-18 | 2023-09-30
| 857 | Willow Creek Apartments | 100 Willow Creek Drive | Mount Juliet | TN | 37122 | 144 | Adam Brookins | Family, S42 | DCAS | N/A | N/A |  | 2022-04-29 | 2023-02-28
1932
Completed - Retention
| 452 | Bluffs at Nine Mile Creek - Refinance - 2021 | 7475 Flying Cloud Drive | Eden Prairie | MN | 55344 | 188 | Bill Buelow | N/A | DCAS | BKV | Liza Kapisak |  | 2021-06-11 | 2023-03-02
| 830 | Swiss Ridge | 455 Swiss Ave | Nashville | TN | 37211 | 84 | Adam Brookins | Family, Garden, S42 | DCAS | N/A | N/A |  | 2021-06-17 | 2022-12-01
272
Pending
| 876 | The Springs Apartments | 289 Springs Lane | Dripping Springs | TX | 78620 | 76 | Adam Brookins | Family, S42 | DCAS | TBD | TBD |  | 2026-01-01 | 2027-01-01
| 861 | Sandy Creek - Pre-Rehab Scope | 1828 Sandy Point Road | Bryan | TX | 77807 | 140 | Adam Brookins | N/A | TBD | N/A | N/A |  | 2022-10-24 | 2022-11-30
216
|  | Self Performed Project Subtotal |  |  |  |  | 2420
|  | Active Projects Total |  |  |  |  | 7838
|  | Pending Projects Total |  |  |  |  | 9109
|  | Subtotal |  |  |  |  | 16947
|  | Completed/Retention Remainining Total |  |  |  |  | 2973
|  | Grand Total |  |  |  |  | 19920